## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE: BeeKey
Enter Company Name in cell B2. | Company Name: BTree
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead: Do Vuong Phuc |  |  | Project Start: |  |  | 2021-05-28
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  | Display Week: |  |  | 1 |  |  | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-05-24 to 2021-07-18
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | SHORT DESCRIPTION | ASSIGNED ID | ASSIGNED TO | DURATION (DAY) | PROGRESS | START | END | DAYS | time axis 2021-05-24 to 2021-07-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Sprint 0
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Kick-off meeting | Explain the project, training course and brainstorm the project idea to write proposal | 1 | Đỗ Vương Phúc | 0 | 100% | 2021-05-28 | 2021-05-28 | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Self-learning A | Learn about Android studio (Unit 1, 2) | 1 | Đỗ Vương Phúc | 10 | 100% | 2021-05-28 | 2021-06-07 | 11
| Self-learning A | Learn about Android studio (Unit 1, 2) | 2 | Hoàng Như Thanh | 10 | 100% | 2021-05-28 | 2021-06-07 | 11
| Self-learning A | Learn about Android studio (Unit 1, 2) | 3 | Chung Kim Khánh | 10 | 100% | 2021-05-28 | 2021-06-07 | 11
| Self-learning A | Learn about Android studio (Unit 1, 2) | 4 | Bùi Đăng Khoa | 10 | 100% | 2021-05-28 | 2021-06-07
| Design logo | Design application and team logo | 2 | Hoàng Như Thanh | 7 | 100% | 2021-05-28 | 2021-06-04
| Project Proposal | Write project proposal | 3 | Chung Kim Khánh | 7 | 100% | 2021-05-28 | 2021-06-04 | 8
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Sprint 1
| Sprint planning meeting | Planning for all sprints and explain for team | 1 | Đỗ Vương Phúc | 0 | 100% | 2021-06-07 | 2021-06-07 | 1
| Self-learning B | Learn about Android studio (Unit 3, 4) | 2 | Hoàng Như Thanh | 10 | 100% | 2021-06-07 | 2021-06-17 | 11
| Self-learning B | Learn about Android studio (Unit 3, 4) | 3 | Chung Kim Khánh | 10 | 100% | 2021-06-07 | 2021-06-17 | 11
| Self-learning B | Learn about Android studio (Unit 3, 4) | 4 | Bùi Đăng Khoa | 10 | 100% | 2021-06-07 | 2021-06-17 | 11
| Self-learning D | Learn NodeJS, JWT, Express to build server | 1 | Đỗ Vương Phúc | 10 | 100% | 2021-06-07 | 2021-06-17
| Project plan (1-3) | Write project plan section 1-3 | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-07 | 2021-06-11
| Project plan (4) | Write project plan section 4 | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-07 | 2021-06-11
| Vision document (1-3) | Write vision document section 1-3 | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-07 | 2021-06-11
| Vision document (4-6) | Write vision document section 4-6 | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-07 | 2021-06-11
| Weekly report 1 | Note down and write the weekly report | 3 | Chung Kim Khánh | 2 | 100% | 2021-06-11 | 2021-06-13
| Weekly report 2 | Note down and write the weekly report and submit PA1 | 3 | Chung Kim Khánh | 1 | 100% | 2021-06-18 | 2021-06-19
| Login UI | Prototype, implement login UI for user to login | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-14 | 2021-06-18
| Sign up UI | Prototype, implement sign up UI for user to sign up an account | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-14 | 2021-06-18
| Show information UI | Prototype, implement show information UI to display the information of user | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-14 | 2021-06-18
| Setting UI | Prototype, implement setting UI to navigate to different activity (change information, password, report, logout) | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-14 | 2021-06-18
| Change password UI | Prototype, implement change password UI for user to update their password | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-14 | 2021-06-18
| Change information UI | Prototype, implement change information UI for user to change basic information (display name, gender, phone and address) | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-14 | 2021-06-18
| Design database | Prototype ERD and implement SQL source then setup the server | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
| Login API | Create login API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
| Sign up API | Create signup API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
| Get information API | Create get the information of user API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
| Change password API | Create change password API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
| Change information API | Create change basic information of user API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-14 | 2021-06-18
Sample phase title block | Sprint 2
| Revised Project Plan | Revised and update project plan | 3 | Chung Kim Khánh | 6 | 100% | 2021-06-19 | 2021-06-25 | 7
| Detail Vision Document | Revise and write more detail the vision document | 1 | Đỗ Vương Phúc | 6 | 100% | 2021-06-19 | 2021-06-25 | 7
| Use-case model | Design and draw use-case model | 2 | Hoàng Như Thanh | 6 | 100% | 2021-06-19 | 2021-06-25 | 7
| Use-case specification | Write the use-case specification base on the model | 4 | Bùi Đăng Khoa | 6 | 100% | 2021-06-19 | 2021-06-25 | 7
| Weekly report 1 | Note down and write the weekly report | 2 | Hoàng Như Thanh | 2 | 100% | 2021-06-25 | 2021-06-27
| Weekly report 2 | Note down and write the weekly report and submit PA2 | 2 | Hoàng Như Thanh | 1 | 100% | 2021-07-02 | 2021-07-03
| Self learning C | Learn about MVC model and Android studio (unit 3, 4) | 1 | Đỗ Vương Phúc | 11 | 100% | 2021-06-19 | 2021-06-30
| Self learning C | Learn about MVC model and Android studio (unit 3, 4) | 2 | Hoàng Như Thanh | 11 | 100% | 2021-06-19 | 2021-06-30
| Self learning C | Learn about MVC model and Android studio (unit 3, 4) | 3 | Chung Kim Khánh | 11 | 100% | 2021-06-19 | 2021-06-30
| Self learning C | Learn about MVC model and Android studio (unit 3, 4) | 4 | Bùi Đăng Khoa | 11 | 100% | 2021-06-19 | 2021-06-30
| Post task UI | Prototype, implement post task UI for user to create a new task | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-28 | 2021-07-02
| Task filter UI | Prototype, implement task filter UI to display all the task with the specified category | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-28 | 2021-07-02
| Counter-offer UI | Prototype, implement counter-offer UI for user to make a counter-offer when viewing a posted task | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-28 | 2021-07-02
| Report UI | Prototype, implement report UI for user to report an issue | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-28 | 2021-07-02
| My request UI | Prototype, implement my request UI for user to view the list of their requests | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-28 | 2021-07-02
| My task UI | Prototype, implement my task UI for user to view the list of their tasks | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-28 | 2021-07-02
| Implement signup | Implement feature of signup UI | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-28 | 2021-07-02
| Implement login | Implement feature of login UI | 4 | Bùi Đăng Khoa | 4 | 100% | 2021-06-28 | 2021-07-02
| Implement show information | Implement feature of show information UI | 2 | Hoàng Như Thanh | 4 | 0% | 2021-06-28 | 2021-07-02
| Implement setting | Implement feature of setting UI | 2 | Hoàng Như Thanh | 4 | 100% | 2021-06-28 | 2021-07-02
| Implement change password | Implement feature of change password UI | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-28 | 2021-07-02
| Implement change information | Implement feature of change information UI | 3 | Chung Kim Khánh | 4 | 100% | 2021-06-28 | 2021-07-02
| Post task API | Create post a task API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
| Get request by filter API | Create get requests with category API in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
| Add counter-offer API | Create API to add counter-offer of a task in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
| Report API | Create API to make a report in server and update API sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
| Get user request API | Create API to get all requests of a user and update sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
| Get user task API | Create API to get all tasks of a user and update sheet | 1 | Đỗ Vương Phúc | 4 | 100% | 2021-06-28 | 2021-07-02
Sample phase title block | Sprint 3
| Revised use-case specification | Revise use-case model and specification | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-10 | 2021-07-16 | 7
| Define software architecture (SAD) | Write define software architecture document | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-10 | 2021-07-16 | 7
| Class diagram | Draw class diagram | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-10 | 2021-07-16 | 7
| Weekly report 1 | Note down and write the weekly report | 1 | Đỗ Vương Phúc | 4 | 0% | 2021-07-10 | 2021-07-14
| Weekly report 2 | Note down and write the weekly report and submit PA3 | 1 | Đỗ Vương Phúc | 1 | 0% | 2021-07-23 | 2021-07-24
| Request view UI | Prototype, implement the activity to view the request UI | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-17 | 2021-07-23
| Task view UI | Prototype, implement the activity to view the task UI | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-17 | 2021-07-23
| Counter list UI | Prototype, implement the activity to view all the counter list of my request UI | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-17 | 2021-07-23
| Feedback UI | Prototype, implement the feedback UI | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-17 | 2021-07-23
| Chatting UI | Prototype, implement chatting UI | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-17 | 2021-07-23
| Top-up UI | Prototype, implement top-up UI | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement post task | Implement feature to create a new task | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement task filter | Implement feature to display all the task filtered by category | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement counter-offer | Implement feature to make a counter-offer when viewing a task | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement report | Implement feature to create a report for an issue | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement my request | Implement feature to display the list of my request | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement my task | Implement feature to display the list of my task | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-17 | 2021-07-23
| Implement top-up | Implement feature for user to top-up money from banking | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23
| Get request API | Create API to get the information of a request and update sheet | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23
| Get task API | Create API to get the information of a task and update sheet | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23
| Get all counter of request API | Create API to get all the counter-offer of a request and update sheet | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23 | 7
| Top-up API | Create API for user to top-up money and verify with banking system | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23
| Accept/Decline counter API | Create API to accept or decline a counter-off API | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-17 | 2021-07-23 | 7
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Sprint 4
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | UI Prototype | Draw and combine all the UI prototype above | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-24 | 2021-07-30
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Revise SAD | Revise SAD document | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-24 | 2021-07-30
| Weekly report 1 | Note down and write the weekly report | 4 | Bùi Đăng Khoa | 2 | 0% | 2021-07-30 | 2021-08-01
| Weekly report 2 | Note down and write the weekly report and submit PA4 | 4 | Bùi Đăng Khoa | 1 | 0% | 2021-08-06 | 2021-08-07
| Implement request view | Implement feature to view one of my requests | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-31 | 2021-08-06
| Implement task view | Implement feature to view one of my task | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-07-31 | 2021-08-06
| Implement counter list | Implement feature to display the counter-offer list of a request | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-31 | 2021-08-06
| Implement feedback | Implement feature to make feedback after done | 3 | Chung Kim Khánh | 6 | 0% | 2021-07-31 | 2021-08-06
| Implement chatting | Implement feature to chat between two users | 2 | Hoàng Như Thanh | 6 | 0% | 2021-07-31 | 2021-08-06
| Feedback API | Create feedback API (Include get feedback of a user, make a feedback) and update sheet | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-31 | 2021-08-06
| Chatting API | Create chatting API (Include send message and load message) and update sheet | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-07-31 | 2021-08-06
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Sprint 5
| Test plan and test case | Write test plan document and testcase | 2 | Hoàng Như Thanh | 5 | 0% | 2021-08-08 | 2021-08-13
| Automated testing | Write automated test | 1 | Đỗ Vương Phúc | 5 | 0% | 2021-08-08 | 2021-08-13
| Weekly report 1 | Note down and write the weekly report | 3 | Chung Kim Khánh | 2 | 0% | 2021-08-13 | 2021-08-15
| Weekly report 2 | Note down and write the weekly report and submit PA5 | 3 | Chung Kim Khánh | 1 | 0% | 2021-08-20 | 2021-08-21
| Test login | Test and fix to be accepted bases on test plan | 3 | Chung Kim Khánh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test signup | Test and fix to be accepted bases on test plan | 3 | Chung Kim Khánh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test change password | Test and fix to be accepted bases on test plan | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-08-14 | 2021-08-20
| Test change basic information | Test and fix to be accepted bases on test plan | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-08-14 | 2021-08-20
| Test view information | Test and fix to be accepted bases on test plan | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-08-14 | 2021-08-20
| Test view list request with filter | Test and fix to be accepted bases on test plan | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-08-14 | 2021-08-20
| Test top-up | Test and fix to be accepted bases on test plan | 4 | Bùi Đăng Khoa | 6 | 0% | 2021-08-14 | 2021-08-20
| Test upload new request | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test make counter-offer | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test view list counter-offer of a request | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test accept/decline a counter-offer | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test chatting | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test done a request | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test feedback | Test and fix to be accepted bases on test plan | 2 | Hoàng Như Thanh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test view my list request | Test and fix to be accepted bases on test plan | 3 | Chung Kim Khánh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test view my list task | Test and fix to be accepted bases on test plan | 3 | Chung Kim Khánh | 6 | 0% | 2021-08-14 | 2021-08-20
| Test logout | Test and fix to be accepted bases on test plan | 3 | Chung Kim Khánh | 6 | 0% | 2021-08-14 | 2021-08-20
| Develop the rest task | Develop the task that have not done | 1 | Đỗ Vương Phúc | 6 | 0% | 2021-08-14 | 2021-08-20
Sample phase title block | Sprint 6
| Project presentation | Presentation the project to the stakeholder and lecturer | 1 | Đỗ Vương Phúc | 1 | 0% | 2021-08-21 | 2021-08-22
| Project presentation | Presentation the project to the stakeholder and lecturer | 2 | Hoàng Như Thanh | 1 | 0% | 2021-08-21 | 2021-08-22
| Project presentation | Presentation the project to the stakeholder and lecturer | 3 | Chung Kim Khánh | 1 | 0% | 2021-08-21 | 2021-08-22
| Project presentation | Presentation the project to the stakeholder and lecturer | 4 | Bùi Đăng Khoa | 1 | 0% | 2021-08-21 | 2021-08-22
| Final submission | Submit the PA6 to moodle | 1 | Đỗ Vương Phúc | 1 | 0% | 2021-08-21 | 2021-08-22
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## Member
No | Name
1 | Đỗ Vương Phúc
2 | Hoàng Như Thanh
3 | Chung Kim Khánh
4 | Bùi Đăng Khoa

## Sheet1
2021-07-17 | 2021-07-10
2021-07-17 | 2021-07-10
2021-07-17 | 2021-07-10
2021-07-17 | 2021-07-10
2021-07-30 | 2021-07-23
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
2021-07-24 | 2021-07-17
1900-01-06 | 1900-01-06
2021-07-31 | 2021-07-24
2021-07-31 | 2021-07-24
2021-08-06 | 2021-07-30
2021-08-13 | 2021-08-06
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
2021-08-07 | 2021-07-31
1900-01-06 | 1900-01-06
2021-08-15 | 2021-08-08
2021-08-15 | 2021-08-08
2021-08-20 | 2021-08-13
2021-08-27 | 2021-08-20
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
2021-08-21 | 2021-08-14
1900-01-06 | 1900-01-06
2021-08-28 | 2021-08-21
2021-08-28 | 2021-08-21
2021-08-28 | 2021-08-21
2021-08-28 | 2021-08-21
2021-08-28 | 2021-08-21
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06
1900-01-06