## Test summary report
Tester list
Tester | ThanhHoang
Date | 2021-08-27
Tester | KhoaBui
Date | 2021-08-23
Tester | CKKhanh
Date | 2021-08-26

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Choose category fail to connect | 1. Login 2. Click post at navigation bar 3. Title = "test ahihi"¦ category = "testing" ¦ description ¦ deadline = "01/01/2022 00:00:00" ¦price = 2 4. Click post button 5. Click search button at navigation bar 6. Category = "testing" Expected: Show your task title = "test ahihi" Actual: Fail connect to server | UC02 | High | KhoaBui | 2021-08-23 | Closed | Ghost bug
B002 | Click self-task cause crashed | 1. Login("client","admin") 2. Click post at navigation bar 3. Title = "test search your self"¦ category = "testing" ¦ description ¦ deadline = "01/01/2022 00:00:00" ¦ price = 2 4. Login("lancer","admin") 5. Click search button at navigation bar 6. Category = "testing" 7. Click task title = "test click your self" Expected: Direct to counter offer screen Actual: Crash application | UC02 | High | KhoaBui | 2021-08-25 | Closed | Month in deadline does not correct
B003 | Post with empty field | "1. Sign Up (Skip if you already have an account) 2. Login (username: "kimkhanh", password: "123456") 3. Click Post icon 4. Click "Post"" Expected: Display toast "Information is empty" Actual: Automatically exit the software | UC01 | High | CKKhanh | 2021-08-26 | Closed | Did not code
B004 | Add a file in "File Attachment" | "1. Sign Up (Skip if you already have an account) 2. Login (username: "kimkhanh", password: "123456") 3. Click Post icon 4. Fill the informations (Title: "Teky workplace app", Description: "Tôi đến từ...", Category: "Mobile application", Deadline: "30/10/2021 - 23h57", File Attachment "file.txt", Starting at $: "30000") 5. Click "Post"" Expected: Can add one or more than one file Actual: Can click on the file but the file is not added | UC01 | High | CKKhanh | 2021-08-26 | Open | Will not fix
B005 | Post without the "Title" | "1. Sign Up (Skip if you already have an account) 2. Login (username: "kimkhanh", password: "123456") 3. Click Post icon 4. Fill the informations (Description: "Hi", Category: "Testing", Deadline: "30/09/2021 - 23h57", Starting at $: "20000") 5. Click "Post"" Expected: Display toast "Title is empty" Actual: Display toast "Successful" | UC01 | High | CKKhanh | 2021-08-26 | Closed | B003
B006 | Post without the "Starting at $" | "1. Sign Up (Skip if you already have an account) 2. Login (username: "kimkhanh", password: "123456") 3. Click Post icon 4. Fill the informations (Title: "Hello", Description: "Hi", Category: "Testing", Deadline: "30/09/2021 - 23h57") 5. Click "Post"" Expected: Display toast "Price is empty" Actual: Automatically exit the software | UC01 | High | CKKhanh | 2021-08-26 | Closed | B003
B007 | Post a valid request then post another valid request | "1. Sign Up (Skip if you already have an account) 2. Login (username: "kimkhanh", password: "123456") 3. Click Post icon 4. Fill the informations (Title: "Teky workplace app", Description: "Tôi đến từ...", Category: "Mobile application", Deadline: "30/10/2021 - 23h57", File Attachment "file.txt", Starting at $: "30000") 5. Click "Post" 6. Click Post icon again" Expected: Open a new empty form Actual: Open the old form before | UC01 | High | CKKhanh | 2021-08-26 | Closed | B003
B008 | Text not clickable | "1. Launch application 2. Login with an account that already has tasks 3. On profile screen, click ""My Task""" Expected: Task view screen displays like this https://www.figma.com/file/dE0cjjEuyJ0JiXDoXRHbjg/BeeKey?node-id=144%3A1150 Actual: Must click on the blue icon on the left of the text "On-going task" to navigate to My Task view. The screen displayed with wrong text "Request view". | UC03 | High | ThanhHoang | 2021-08-27 | Closed
B009 | Incorrect text for My Task view | "1. Launch application 2. Login with an account that already has task 3. On profile screen, click "My Task" 4. When "My Task" screen displays, click on any task" Expected: Task detail screen displays including title, discription, deadline, status, offer, client username and "CHAT" button. See on figma: https://www.figma.com/file/dE0cjjEuyJ0JiXDoXRHbjg/BeeKey?node-id=305%3A1857" Actual: The screen displays with wrong text "Request view" and "Counter task". | UC03 | Low | ThanhHoang | 2021-08-27 | Closed
B010 | Toast does not display | "1. Launch application 2. Login with an account that do not have task 3. On profile screen, click ""My Task"" Expected: Display toast "You have not achieved any task" Actual: Toast does not display | UC03 | Low | ThanhHoang | 2021-08-27 | Closed
B011 | Toast does not display | "1. Launch application 2. Login with an account that do not have request 3. On profile screen, click "My Request"" Expected: Display toast "You have not posted any request" Actual: Toast does not display | UC03 | Low | ThanhHoang | 2021-08-27 | Closed
B012 | List request does not in order | "1. Launch application 2. Login with an account that has many requests whose status are different 3. On profile screen, click "My Request"" Expected: Show in order ON-GOING, PENDING, DONE Actual: Show in order DONE, ON-GOING, PENDING | UC03 | Low | ThanhHoang | 2021-08-29 | Closed